## RMI
RMI
Name | Status | Period | Indicator | Pathway | Description
Outputs
Convening hosted to kick off the Shoonya campaign | Completed | 2021-First Half | Trainings/Webinars/Seminars | Improve awareness & adoption of EV | RMI was responsible for the conceptualization and launch of the Shoonya campaign, in partnership with Niti Aayog. The convening launched the campaign, with 35 companies pledging support to the campaign. No evidence Date: April 2021
Report on barriers and challenges to financing EVs in India | Completed | 2021-First Half | Policy recommendations | Reduce financial barriers | This report highlights financing as a key hurdle to accelerating uptake of EVs, providing a snapshot of the key challenges faced (such as high interest and insurance rates, low loan-to-value ratios, and limited specialized financing options).
Internal documentation and support to DHI on the FAME scheme- Document 3 | Completed | 2021-First Half | Policy implementation request | Unlocking policy & regulatory barriers | No details on the nature of the content. Part of three internal documents provided to DHI on the FAME Scheme.
Internal documentation and support to DHI on the FAME scheme- Document 2 | Completed | 2021-First Half | Policy implementation request | Unlocking policy & regulatory barriers | No details on the nature of the content. Part of three internal documents provided to DHI on the FAME Scheme.
[Central] Implementation recommendations for battery storage mission | Completed | 2021-First Half | Policy recommendations | Unlocking policy & regulatory barriers | This internal report served as a guide for NITI Aayog to operationalise the PLI scheme and has resulted in the publication of two publicly available reports. Note: Date of submission is not available. This will be double counted alongside publications. This served as policy guidance that was later turned into 3 reports. No evidence available
[Central] Production Linked Incentive (PLI) scheme (‘National Programme on Advanced Chemistry Cell (ACC) Battery Storage') | Completed | 2021-First Half | Policy recommendations | Unlocking policy & regulatory barriers | RMI was the lead technical advisor for NITI Aayog to develop the scheme. The scheme aims to support the creation of 50 GWh of domestic manufacturing capacity for ACC batteries and 5 GWh per year of ""niche"" ACC batteries. Date of submission is probably in first half of Reporting year 1 (it was approved by the govt in July 2021)
[State] EV Policy Maharashtra submitted to state government | Completed | 2021-First Half | Policy recommendations | Unlocking policy & regulatory barriers | As an extension to the broader EV Accelerator, RMI has deepened engagement in Maharashtra. RMI provided technical assistance not just to formulae the state’s EV policy, but also to support its notification and operationalisation. This included India’s first-ever state level ZEV credit program. Technical inputs were provided on fiscal incentives, budget outlay, non-fiscal incentives and other policy provisions. Submitted to state government in March 2021 Note: no evidence of submission
[Central Level] EV Policy Accelerator | Completed | 2021-First Half | Policy recommendations | Unlocking policy & regulatory barriers | This technical assistance platform was launched in partnership with NITI Aayog. The goal has been to provide technical assistance to states and union territories on the development of EV policies that work in tandem with the centrally sponsored FAME scheme. RMI provided technical assistance to 11 states. Launched in March 2021 Note: no evidence available
Mobilising Electric Vehicle Financing in India | Completed | 2021-First Half | Publications | Unlocking policy & regulatory barriers | NITI Aayog and RMI India release a new report ‘Mobilising Electric Vehicle Financing in India"". New Report Proposes Toolkit of Solutions to Lower Cost and Increase Finance for Electric Vehicles
EV Policy Maharashtra | Completed | 2021-First Half | Publications | Unlocking policy & regulatory barriers | The EV policy was submitted to the Maharashtra government in March 2021. Note: Evidence is the actual policy notified later in July 2021 and not the document submitted by RMI (IO level evidence)
Production Linked Incentive (PLI) scheme | Completed | 2021-First Half | Publications | Unlocking policy & regulatory barriers | RMI was the lead technical advisor for NITI Aayog to develop the scheme. The scheme aims to support the creation of 50 GWh of domestic manufacturing capacity for ACC batteries and 5 GWh per year of ""niche"" ACC batteries. This Result is the external documentation of the policy (notification).
EV Accelerator Workshop | Completed | 2021-Second Half | Convenings/workshops | Unlocking policy & regulatory barriers | RMI, along with PMC, hosted the Pune City EV Accelerator Workshop. The intention has been to fast-track EV adoption, and the inputs from the workshop informed the drafting of Pune’s City EV readiness plan. Date: December 2021 No evidence
Pune Ad-hoc Support: EV Cell | Completed | 2021-Second Half | Policy implementation request | Unlocking policy & regulatory barriers | RMI and Pune Municipal Corporation set up India's first ever EV cell in Pune to facilitate coordination amongst stakeholders
Memo for operationalization of the Charging expression of interest (EOI) for DHI | Completed | 2021-Second Half | Policy implementation request | Unlocking policy & regulatory barriers | A memo for operationalization of the Charging expression of interest (EOI) floated was submitted to DHI. The memo includes initial analysis, proposes a national convening, and a process for operationalization of the EOI in select cities. Note: internal memo, no evidence available
EV Policy Himachal Pradesh | Completed | 2021-Second Half | Publications | Unlocking policy & regulatory barriers | Himachal Pradesh notified its EV Policy based (linked to RMI's role in the State EV Accelerator). Note: need to request RMI for evidence of inputs provided. Evidence uploaded is of the EV policy being notified by Himachal Pradesh. Need to also confirm date.
Banking on Electric Vehicles in India- A Blueprint for Inclusion of EVs in Priority Sector Lending Guidelines | Completed | 2022-First Half | Policy recommendations | Reduce financial barriers | The paper looks at including EVs in the Reserve Bank of India’s priority sector lending (PSL) guidelines, potentially complementing the NITI Aayog and World Bank’s USD 300 million first-loss-risk-sharing facility and also encouraging the financial sector to mobilize necessary capital. Date: January 2022
Pune Ad-hoc Support: EV Cell Website | Completed | 2022-First Half | Policy implementation request | Unlocking policy & regulatory barriers | Supported the development of the Pune city EV cell webpage that acts as a knowledge depository of EV initiatives, and tracks EV sales and charging infrastructure deployment in the city.
Pune Ad-hoc Support: EV Awareness campaign | In Process | 2022-First Half | Policy implementation request | Unlocking policy & regulatory barriers | Supporting Pune in designing a city-level EV awareness campaign to convey the environmental, social, and economic benefits of EVs to the citizens.
Pune Ad-hoc Support: Charging infrastructure Support to PMC | In Process | 2022-First Half | Policy implementation request | Unlocking policy & regulatory barriers | Working with the PMC team to prepare a phase-wise city-level charging infrastructure plan to deploy 500 charging points and 625 swapping points across the city.
National database on charging stations | Completed | 2022-First Half | Policy implementation request | Unlocking policy & regulatory barriers | This is an internal document. Description: National database on charging stations and a public tool for discovering charging stations across the country Note: no evidence available, nor date of submission.
Global comparative analysis of charging standards for DHI | Completed | 2022-First Half | Policy implementation request | Unlocking policy & regulatory barriers | This is an internal document. Description: Global comparative analysis of charging standards for DHI Note: no evidence available, nor date of submission.
[Central/State] Engagement with EESL and DISCOMs in Delhi for charging infrastructure | Completed | 2022-First Half | Policy recommendations | Unlocking policy & regulatory barriers | Engagement with EESL and CESL in Delhi for 3 key workstreams – charging infrastructure, interest subvention scheme, EV leasing scheme. No evidence, dates not available.
[City Level] Pune’s City EV Readiness Plan | Completed | 2022-First Half | Policy recommendations | Unlocking policy & regulatory barriers | RMI provided technical assistance to launch the plan in April 2022. The plan focuses on providing specific solutions to domain areas (such as EV charging and battery swapping, awareness programs, and easing EV operations). It is the first of its kind developed for a city in India.
[City level] Roadmap for Delivery Electrification | Completed | 2022-First Half | Publications | Unlocking policy & regulatory barriers | This report highlights insights from the design, implementation, and consultation phases of the Deliver Electric Delhi Pilot, and compiles these findings into a roadmap for scaling final-mile delivery vehicle adoption. The Pilot identified ways in which policies, charging infrastructure, and access to finance can help private and public sector players fully electrify final-mile delivery vehicles. The report compares the costs and performance of EVs to their fossil fuel counterparts and outlines the economic case for fleet electrification. Note: date not available
[City] Pune’s City EV Readiness Plan | Completed | 2022-First Half | Publications | Unlocking policy & regulatory barriers | RMI provided technical assistance to launch the plan in April 2022. The plan focuses on providing specific solutions to domain areas (such as EV charging and battery swapping, awareness programs, and easing EV operations). It is the first of its kind developed for a city in India. Note: this will be double counted with the policy indicator Date: April 2022
[City] Pioneering Electric Buses in Pune | Completed | 2022-First Half | Publications | Unlocking policy & regulatory barriers | RMI worked on a case study, focusing on Pune city and documenting the city’s experience of operating and procuring 650 electric buses. This involved consultations with stakeholders, focusing on e-bus procurement and challenges around financing. Note: This will be double counted alongside the policy recommendation indicator Date: April 2022
The Need for Advanced Chemistry Energy Storage Cells in India Part I of III | Completed | 2022-First Half | Publications | Unlocking policy & regulatory barriers | This report is part 1 of a three series reporting produced as a result of internal support provided by RMI to Niti Aayog. Description of report: This report estimates India’s future demand for batteries under two scenarios: an “accelerated” scenario and a “conservative” scenario. The accelerated scenario assumes the current policy momentum for EVs, renewables, and other end-use applications. This will trigger the market and lead to high penetration of these technologies. In the accelerated scenario, battery demand rises in line with expected success of India’s ambitions and incentives around vehicle electrification and grid decarbonization. The conservative scenario assumes battery demand rises in line with the most conservative expert forecasts. Date: February 2022
Navi Mumbai Ad-hoc Support: Technical Assistance MoU with Navi Mumbai Municipal Corporation | Completed | 2022-Second Half | Policy implementation request | Unlocking policy & regulatory barriers | Signing an MoU with Navi Mumbai Municipal Corporation to provide technical assistance in their EV projects, including setting up of EV Cell, and preparation and implementation of EV readiness plan, etc.
Pune Ad-hoc Support: Drafting and submitting proposals | In Process | 2022-Second Half | Policy implementation request | Unlocking policy & regulatory barriers | Supported in drafting and submitting proposals for several competitions such as Bloomberg Global Mayors Challenge, Skotch Awards 2022, Bloomberg C40 Awards 2022, WRI Ross Prize for cities
Pune Ad-hoc Support: Day to day management of activities | In Process | 2022-Second Half | Policy implementation request | Unlocking policy & regulatory barriers | Supporting the day-to-day activities – conducting EV cell meetings at regular intervals, hosting industry convenings, implementing Maharashtra EV policy measures, etc.
Pune Ad-hoc Support: Implementation of Maharashtra EV Policy | In Process | 2022-Second Half | Policy implementation request | Unlocking policy & regulatory barriers | Supporting Pune in implementing Maharashtra EV Policy’s provisions viz., building byelaws, parking preference for EVs, property tax rebates on private charging infrastructure, etc.
Pune Ad-hoc Support: Finance Utilization Plan | Completed | 2022-Second Half | Policy implementation request | Unlocking policy & regulatory barriers | Supported Pune city in preparing a detailed utilization plan for the INR 250 crore received under the XV Finance Commission by the Central Government.
Ad-hoc support to 11 states as part of the EV Accelerator | In Process | 2022-Second Half | Policy implementation request | Unlocking policy & regulatory barriers | Informed the EV policies of 11 states as part of the EV policy accelerator Note: we don't have specific instances of support provided to the states. This is, for now, listed as a broad category. We need to decide if we can ask partners to document each ad hoc support provided along with date and evidence
Need for Advanced Chemistry Cell Energy Storage in India Part 2 |  | 2022-Second Half | Publications | Unlocking policy & regulatory barriers | This report is part 2 of a three series reporting produced as a result of internal support provided by RMI to Niti Aayog. Description of Report: The report analyses existing, advanced, and upcoming battery technologies on multiple industry standard performance metrics, and provides an outlook of battery chemistries that could go mainstream by 2030 and beyond. It also highlights the key characteristics of various battery technologies, their pros and cons, and their suitability for key applications. India has the perfect opportunity to establish a battery manufacturing ecosystem on the foundation of new technologies that leverage abundantly available indigenous materials like sodium and aluminium. Note: Need date from RMI
Internal documentation and support to DHI on the FAME scheme- document 1 | Completed | null-null | Policy implementation request | Unlocking policy & regulatory barriers | No details on the nature of the content. Part of three internal documents provided to DHI on the FAME Scheme.
Int. Outcomes
[Convening/workshop] Convening with stakeholders in Pune to develop the ‘Pioneering Electric Buses in Pune’ case study | Completed | 2021-Second Half | Policy dialogues | Reduce financial barriers | Convenings and consultations were held with stakeholders, including the Pune Municipal Corporation (PMC), Pune Mahanagar Parivahan Mahamandal Limited (PMPML), and Pune Smart City Development Corporation Limited. Note: Have marked this as one lump sum sort of ‘convening’ for the dashboard. Don’t think RMI will have details for each consultation, or if each then would count towards separate results? No evidence, but overlap with the publication that was produced as a result of this engagement